## Main
Product | School Connect Application |  | Product Status | New Project
Active versions | 1 |  | Sponsor | Nguyen Minh Nhat
Team |  |  | Product Owner | Nguyen Trung Hieu
Scrum Master | Nguyen Thanh Phu |  |  | Dang Nguyen Bao Hoai
Developers | Nguyen Trung Hieu |  | Project Champion
| Dang Nguyen Bao Hoai |  | Other Stakeholders | Nguyễn Thị Minh Huệ
Projects | [5 empty] | Sprint Plan |  | Project #1
Id | Description | Start | End | Status | Remarks | Sprint | Start | End | Status | Story Points (Committed) | Story Points (Delivered) | Remarks
1 | Initial release | 2021-08-18 | 2021-09-05 | Done |  | 1 | 2021-09-06 | 2021-10-03 | Done | 210 | 213
1.1 | Project’s Kick-off Meeting | 2021-08-18 | 2021-08-22 | Done |  | 2 | 2021-10-04 | 2021-10-31 | Done | 210 | 233
1.2 | Proposal | 2021-08-19 | 2021-08-20 | Done |  | 3 | 2021-11-01 | 2021-11-21 | Done | 157.5 | 159
1.3 | Research technical | 2021-08-20 | 2021-08-30 | Done |  | 4 | 2021-11-22 | 2021-12-12 | Done | 157.5 | 160
1.4 | Project plan | 2021-08-31 | 2021-09-01 | Done
1.5 | Product backlog | 2021-09-02 | 2021-09-03 | Done
1.6 | User story | 2021-09-04 | 2021-09-05 | Done
2 | Development | 2021-09-06 | 2021-12-12 | Done
2.1 | Sprint 1 | 2021-09-06 | 2021-10-03 | Done
2.2 | Sprint 2 | 2021-10-04 | 2021-10-31 | Done
2.3 | Sprint 3 | 2021-11-01 | 2021-11-21 | Done
2.4 | Sprint 4 | 2021-11-22 | 2021-12-12 | Done
3 | Close project | 2021-12-13 | 2021-12-15 | Done

## Sprint Task 1
Ahead Schedule
Sprint Task 1 | [10 empty] | End Task
[11 empty] | Late | [16 empty] | <- effort / day ->
Sprint Id | Backlog Id | Description | Owner | Start-Day | End-Day | Status | Story Points (Est.) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28
Sprint-1 |  |  | Team | 2021-09-06 | 2021-10-03 |  |  |  |  | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-17 | 2021-09-18 | 2021-09-19 | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | 2021-10-02 | 2021-10-03
1 |  | Sprint 1 plan meeting | Team | 2021-09-06 | 2021-09-06 | Done | 7.5 | 7.5 | 0 | 2021-09-06: 0
1 |  | Architecture design meeting | Team | 2021-09-07 | 2021-09-07 | Done | 7.5 | 7.5 | 0 | 2021-09-06: 7.5; 2021-09-07: 0
1 |  | Test plan meeting | Team | 2021-09-08 | 2021-09-08 | Done | 7.5 | 7.5 | 0 | 2021-09-06: 7.5; 2021-09-07: 7.5; 2021-09-08: 0
1 |  | Design sprint 1 backlog | Hieu | 2021-09-09 | 2021-09-10 | Done | 7.5 | 5 | 0 | 2021-09-06: 7.5; 2021-09-07: 7.5; 2021-09-08: 7.5; 2021-09-09: 5; 2021-09-10: 0
1 |  | Design test plan document | Hoai | 2021-09-09 | 2021-09-12 | Done | 7.5 | 10 | 0 | 2021-09-06: 7.5; 2021-09-07: 7.5; 2021-09-08: 7.5; 2021-09-09: 5; 2021-09-10: 2.5; 2021-09-11: 2.5; 2021-09-12: 0
1 |  | Design architecture | Phu | 2021-09-09 | 2021-09-15 | Done | 12.5 | 17.5 | 0 | 2021-09-06: 12.5; 2021-09-07: 12.5; 2021-09-08: 12.5; 2021-09-09: 10; 2021-09-10: 10; 2021-09-11: 7.5; 2021-09-12: 7.5; 2021-09-13: 5; 2021-09-14: 2.5; 2021-09-15: 0
1 |  | Design database sprint 1 | Phu | 2021-09-16 | 2021-09-19 | Done | 7.5 | 10 | 0 | 2021-09-06: 7.5; 2021-09-07: 7.5; 2021-09-08: 7.5; 2021-09-09: 7.5; 2021-09-10: 7.5; 2021-09-11: 7.5; 2021-09-12: 7.5; 2021-09-13: 7.5; 2021-09-14: 7.5; 2021-09-15: 7.5; 2021-09-16: 5; 2021-09-17: 5; 2021-09-18: 2.5; 2021-09-19: 0
1 | PB01, PB02, PB11, PB14, PB15, PB17 | Design UI page login admin | Hoai | 2021-09-13 | 2021-09-14 | Done | 10 | 5 | 0 | 2021-09-06: 10; 2021-09-07: 10; 2021-09-08: 10; 2021-09-09: 10; 2021-09-10: 10; 2021-09-11: 10; 2021-09-12: 10; 2021-09-13: 5; 2021-09-14: 0
1 |  | Design UI page login user | Hieu | 2021-09-11 | 2021-09-13 | Done | 10 | 7.5 | 0 | 2021-09-06: 10; 2021-09-07: 10; 2021-09-08: 10; 2021-09-09: 10; 2021-09-10: 10; 2021-09-11: 7.5; 2021-09-12: 5; 2021-09-13: 0
1 |  | Code function login | Phu | 2021-09-20 | 2021-09-25 | Done | 12.5 | 10 | 0 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 10 | 10 | 7.5 | 5 | 2.5 | 0
1 |  | Test case for login | Hoai | 2021-09-15 | 2021-09-17 | Done | 5 | 7.5 | 0 | 2021-09-06: 5; 2021-09-07: 5; 2021-09-08: 5; 2021-09-09: 5; 2021-09-10: 5; 2021-09-11: 5; 2021-09-12: 5; 2021-09-13: 5; 2021-09-14: 5; 2021-09-15: 2.5; 2021-09-16: 2.5; 2021-09-17: 0
1 |  | Design UI homepage admin | Hoai | 2021-09-18 | 2021-09-23 | Done | 12.5 | 15 | 0 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 5 | 5 | 2.5 | 2.5 | 0
1 |  | Design UI homepage | Hieu | 2021-09-14 | 2021-09-19 | Done | 10 | 17.5 | 0 | 2021-09-06: 10; 2021-09-07: 10; 2021-09-08: 10; 2021-09-09: 10; 2021-09-10: 10; 2021-09-11: 10; 2021-09-12: 10; 2021-09-13: 10; 2021-09-14: 7.5; 2021-09-15: 5; 2021-09-16: 2.5; 2021-09-17: 2.5; 2021-09-18: 2.5; 2021-09-19: 0
1 |  | Design UI page Create/edit post | Hieu | 2021-09-20 | 2021-09-22 | Done | 10 | 7.5 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 7.5 | 5 | 0
1 |  | Test case for create/edit post | Hoai | 2021-09-24 | 2021-09-25 | Done | 10 | 5 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 0
1 |  | Code create/edit post | Phu | 2021-09-26 | 2021-09-30 | Done | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 7.5 | 7.5 | 5 | 2.5 | 0
1 |  | Design UI page to add/modify account user information | Hoai | 2021-09-26 | 2021-10-01 | Done | 12.5 | 15 | 0 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 5 | 5 | 2.5 | 2.5 | 0
1 |  | Code add/modify account user information | Phu | 2021-10-01 | N/A | Inprocess | 15 | 2.5 | 12.5 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 12.5 | 12.5 | 12.5
1 |  | Test case for add/modify account user information | Hieu | 2021-09-23 | 2021-09-27 | Done | 10 | 12.5 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 7.5 | 5 | 2.5 | 2.5 | 0
1 |  | Test report sprint 1 | Hieu | 2021-09-28 | 2021-10-01 | Done | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 7.5 | 5 | 2.5 | 0
1 |  | Sprint 1 Review Meeting | Team | 2021-10-02 | 2021-10-02 | Done | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0
1 |  | Sprint 1 Retrospective Meeting | Team | 2021-10-03 | 2021-10-03 | Done | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0
[6 empty] | Esimate | 210 | 210 | 0 | 202.5 | 195 | 187.5 | 180 | 172.5 | 165 | 157.5 | 150 | 142.5 | 135 | 127.5 | 120 | 112.5 | 105 | 97.5 | 90 | 82.5 | 75 | 67.5 | 60 | 52.5 | 45 | 37.5 | 30 | 22.5 | 15 | 7.5 | 0
[6 empty] | Actual | 210 | 214 | 12.5 | 202.5 | 195 | 187.5 | 180 | 172.5 | 167.5 | 162.5 | 150 | 140 | 132.5 | 127.5 | 125 | 122.5 | 110 | 105 | 100 | 92.5 | 85 | 75 | 65 | 62.5 | 52.5 | 47.5 | 40 | 35 | 27.5 | 20 | 12.5
Formulas:
Start-Day = XLOOKUP(0,[Day 1]:[Day 28],L8:AM8)
End-Day = XLOOKUP(0,[Day 1]:[Day 28],L8:AM8)

## Retrospective sprint 1
Retrospective Log Sprint 1
Sprint # | Date | Owner | Continue Doing | Start Doing | Stop Doing | Remarks
1 | 2021-09-09 | Team |  | Redistribute Thang's work to each member of the team | Thang left the group, so each person's work increased more than originally planned
1 | 2021-09-15 | Hiếu |  | The team works together on User Stories documents to report to Mentor | User Story Document still has many problems
1 | 2021-09-18 | Hoài |  | The team works together on Product Backlog documents to report to Mentor | Product Backlog Document still has many problems
1 | 2021-09-29 | Phú |  | The team reduces Phu's work and pre-works some functions to give Phu time to get the job done | Phu's work on the Back end is still slow, slowing down the progress of Sprint 1 on the Front end

## Sprint Task 2
Ahead Schedule
Sprint Task 2 | [10 empty] | End Task
[11 empty] | Late | [16 empty] | <- effort / day ->
Sprint Id | Backlog Id | Description | Owner | Start-Day | End-Day | Status | Story Points (Est.) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28
Sprint-2 |  |  | Team | 2021-10-04 | 2021-10-31 |  |  |  |  | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-05 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31
2 |  | Sprint 2 plan meeting | Team | 2021-10-04 | 2021-10-04 | Done | 7.5 | 7.5 | 0 | 0
2 |  | Sprint 2 backlog | Hieu | 2021-10-05 | 2021-10-06 | Done | 5 | 5 | 0 | 5 | 2.5 | 0
1 | PB15 | Code add/modify account user information | Phu | 2021-10-05 | 2021-10-05 | Done | 12.5 | 15 | 0 | 12.5 | 12.5 | 10 | 7.5 | 5 | 2.5 | 0
2 |  | Design database sprint 2 | Phu | 2021-10-11 | 2021-10-12 | Done | 5 | 5 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2.5 | 0
2 | PB04, PB12, PB16, | Design UI page view post information | Hieu | 2021-10-07 | 2021-10-12 | Done | 12.5 | 17 | 0 | 12.5 | 12.5 | 12.5 | 10 | 10 | 7.5 | 5 | 2.5 | 0
2 |  | Design UI page view account information | Hoai | 2021-10-05 | 2021-10-09 | Done | 12.5 | 12.5 | 0 | 12.5 | 10 | 7.5 | 5 | 2.5 | 0
2 |  | Code view post information | Phu | 2021-10-13 | 2021-10-16 | Done | 7.5 | 10 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 5 | 2.5 | 0
2 |  | Code view account information | Phu | 2021-10-11 | 2021-10-19 | Done | 7.5 | 5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 5 | 2.5 | 0
2 |  | Design UI page view and create / modify forum information | Hoai | 2021-10-10 | 2021-10-16 | Done | 15 | 17.5 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 10 | 5 | 5 | 2.5 | 2.5 | 0
2 |  | Design UI page censorship post and member | Hieu | 2021-10-13 | 2021-10-21 | Done | 20 | 25 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 17.5 | 15 | 15 | 12.5 | 10 | 7.5 | 5 | 2.5 | 0
2 |  | Test case censorship post and member | Hoai | 2021-10-17 | 2021-10-18 | Done | 7.5 | 5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 5 | 0
2 |  | Code view and create/modify forum information | Phu | 2021-10-20 | 2021-10-22 | Done | 12.5 | 7.5 | 0 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 10 | 5 | 0
2 |  | Code censorship post and member | Phu | 2021-10-23 | 2021-10-25 | Done | 15 | 7.5 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 10 | 5 | 0
2 |  | Design UI comment | Hieu | 2021-10-22 | 2021-10-27 | Done | 17.5 | 15 | 0 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 15 | 12.5 | 10 | 7.5 | 2.5 | 0
2 |  | Design UI page see report post and member in forum | Hoai | 2021-10-19 | 2021-10-24 | Done | 12.5 | 15 | 0 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 7.5 | 5 | 5 | 2.5 | 0
2 |  | Test case see report post and member in forum | Hieu | 2021-10-28 | 2021-10-29 | Done | 7.5 | 5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 5 | 0
2 |  | Test case comment | Hoai | 2021-10-25 | 2021-10-25 | Done | 5 | 2.5 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
2 |  | Code comment | Phu | 2021-10-26 | 2021-10-27 | Done | 7.5 | 5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 5 | 0
2 |  | Code see report post and member in forum | Phu | 2021-10-28 | 2021-10-29 | Done | 7.5 | 5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 5 | 0
2 |  | Test report Sprint 2 | Hoai | 2021-10-26 | 2021-10-29 | Done | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 7.5 | 5 | 2.5 | 0
2 |  | Sprint 2 Review Meeting | Team | 2021-10-30 | 2021-10-30 | Done | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0
2 |  | Sprint 2 Retrospective Meeting | Team | 2021-10-31 | 2021-10-31 | Done | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0
[6 empty] | Estimate | 210 | 210 | 0 | 202.5 | 195 | 187.5 | 180 | 172.5 | 165 | 157.5 | 150 | 142.5 | 135 | 127.5 | 120 | 112.5 | 105 | 97.5 | 90 | 82.5 | 75 | 67.5 | 60 | 52.5 | 45 | 37.5 | 30 | 22.5 | 15 | 7.5 | 0
[6 empty] | Actual | 222.5 | 223 | 0 | 215 | 210 | 202.5 | 195 | 190 | 182.5 | 177.5 | 167.5 | 157.5 | 155 | 147.5 | 145 | 137.5 | 130 | 120 | 115 | 105 | 95 | 87.5 | 77.5 | 67.5 | 55 | 45 | 35 | 27.5 | 15 | 7.5 | 0
Formulas:
Start-Day = XLOOKUP(0,[Day 1]:[Day 28],L8:AM8)
End-Day = XLOOKUP(0,[Day 1]:[Day 28],L8:AM8)

## Retrospective sprint 2
Retrospective Log Sprint 2
Sprint # | Date | Owner | Continue Doing | Start Doing | Stop Doing | Remarks
2 | 2021-10-09 | Phú | Phu speeds up the work on the Back end to keep up with the Front end | Phu promptly corrected errors and pre-made some functions on the Front end side
2 | 2021-10-20 | Hoài |  | Hieu instructs Hoai to complete the faulty functions | Hoai encountered an error while doing some functions that affected Sprint's progress
2 | 2021-10-24 | Hiếu |  | Phu, Hoai reduced Hieu's work to keep up with the project schedule | Hieu doesn't have much time to finish work during Sprint 2
2 | 2021-10-29 | Team | Phu assigns specific work to everyone and motivates people to complete functions and documents | Team accelerates to report Midterm Capstone

## Sprint Task 3
Ahead Schedule
| Sprint Task 3 | [10 empty] | End Task
[12 empty] | Late | [16 empty] | <- effort / day ->
| Sprint Id | Backlog Id | Description | Owner | Start-Day | End-Day | Status | Story Points (Est.) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21
| Sprint-3 |  |  | Team | 2021-11-01 | 2021-11-21 |  |  |  |  | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21
| 3 |  | Sprint 3 plan meeting | Team | 2021-11-01 | 2021-11-01 | Done | 7.5 | 7.5 | 0 | 2021-11-01: 0
| 3 |  | Sprint 3 backlog | Hieu | 2021-11-02 | 2021-11-03 | Done | 5 | 5 | 0 | 2021-11-01: 5; 2021-11-02: 2.5; 2021-11-03: 0
| 3 |  | Design database sprint 3 | Phu | 2021-11-02 | 2021-11-03 | Done | 5 | 5 | 0 | 2021-11-01: 5; 2021-11-02: 2.5; 2021-11-03: 0
| 3 | PB06, PB07, PB08, PB10, PB18, PB19, PB20 | Design UI sent message | Hoai | 2021-11-02 | 2021-11-08 | Done | 15 | 17.5 | 0 | 2021-11-01: 15; 2021-11-02: 15; 2021-11-03: 12.5; 2021-11-04: 10; 2021-11-05: 7.5; 2021-11-06: 5; 2021-11-07: 2.5; 2021-11-08: 0
| 3 |  | Design UI delete post, member, comment, chat box | Hieu | 2021-11-04 | 2021-11-12 | Done | 15 | 22.5 | 0 | 2021-11-01: 15; 2021-11-02: 15; 2021-11-03: 15; 2021-11-04: 12.5; 2021-11-05: 10; 2021-11-06: 10; 2021-11-07: 7.5; 2021-11-08: 7.5; 2021-11-09: 5; 2021-11-10: 5; 2021-11-11: 2.5; 2021-11-12: 0
| 3 |  | Test case sent message | Hoai | 2021-11-09 | 2021-11-10 | Done | 5 | 5 | 0 | 2021-11-01: 5; 2021-11-02: 5; 2021-11-03: 5; 2021-11-04: 5; 2021-11-05: 5; 2021-11-06: 5; 2021-11-07: 5; 2021-11-08: 5; 2021-11-09: 2.5; 2021-11-10: 0
| 3 |  | Test case notify new post | Hieu | 2021-11-13 | 2021-11-13 | Done | 5 | 2.5 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
, | 3 |  | Code sent message | Phu | 2021-11-04 | 2021-11-10 | Done | 12.5 | 17.5 | 0 | 2021-11-01: 12.5; 2021-11-02: 12.5; 2021-11-03: 12.5; 2021-11-04: 12.5; 2021-11-05: 10; 2021-11-06: 7.5; 2021-11-07: 7.5; 2021-11-08: 5; 2021-11-09: 2.5; 2021-11-10: 0
| 3 |  | Code notify new post | Phu | 2021-11-11 | 2021-11-13 | Done | 10 | 7.5 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 7.5 | 2.5 | 0
| 3 |  | Code delete post and member | Phu | 2021-11-14 | 2021-11-15 | Done | 7.5 | 5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 5 | 0
| 3 |  | Code delete comment | Phu | 2021-11-16 | 2021-11-16 | Done | 2.5 | 2.5 | 0 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 0
| 3 |  | Code delete chat box | Phu | 2021-11-17 | 2021-11-17 | Done | 2.5 | 2.5 | 0 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 0
| 3 |  | Design UI notify new message and new post | Hoai | 2021-11-11 | 2021-11-13 | Done | 12.5 | 7.5 | 0 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 7.5 | 5 | 0
| 3 |  | Design UI report message and comment | Hieu | 2021-11-14 | 2021-11-17 | Done | 15 | 10 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 12.5 | 7.5 | 5 | 0
| 3 |  | Test case notify new message | Hoai | 2021-11-14 | 2021-11-16 | Done | 5 | 7.5 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2.5 | 0
| 3 |  | Test case report message and comment | Hieu | 2021-11-18 | 2021-11-19 | Done | 5 | 5 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2.5 | 0
| 3 |  | Code notify new message and new post | Phu | 2021-11-18 | 2021-11-18 | Done | 2.5 | 2.5 | 0 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 0
| 3 |  | Code report message and comment | Phu | 2021-11-19 | 2021-11-19 | Done | 2.5 | 2.5 | 0 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 0
| 3 |  | Test report sprint 3 | Hoai | 2021-11-17 | 2021-11-19 | Done | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 5 | 2.5 | 0
| 3 |  | Sprint 3 Review Meeting | Team | 2021-11-20 | 2021-11-20 | Done | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0
| 3 |  | Sprint 3 Retrospective Meeting | Team | 2021-11-21 | 2021-11-21 | Done | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0
[7 empty] | Esimate | 157.5 | 157.5 | 0 | 150 | 142.5 | 135 | 127.5 | 120 | 112.5 | 105 | 97.5 | 90 | 82.5 | 75 | 67.5 | 60 | 52.5 | 45 | 37.5 | 30 | 22.5 | 15 | 7.5 | 0
[7 empty] | Actual | 157.5 | 159 | 0 | 150 | 145 | 137.5 | 132.5 | 125 | 120 | 115 | 110 | 102.5 | 97.5 | 87.5 | 77.5 | 65 | 60 | 47.5 | 40 | 30 | 22.5 | 15 | 7.5 | 0
Formulas:
Start-Day = XLOOKUP(0,[Day 1]:[Day 21],L8:AF8)
End-Day = XLOOKUP(0,[Day 1]:[Day 21],L8:AF8)

## Retrospective sprint 3
Retrospective Log Sprint 2
Sprint # | Date | Owner | Continue Doing | Start Doing | Stop Doing | Remarks
3 | 2021-11-05 | Phú |  | The team agreed to increase the team meeting time to help each other complete the work and carry out the next work | Make an appointment with a mentor who is having a hard time because the mentor is busy
3 | 2021-11-11 | Phú | Migrating the source code repository from Bitbucket to Github makes it possible to complete some functions faster, easier and convenient to use | Phu proposes to move the source code repository from Bitbucket to Github to facilitate some functions
3 | 2021-11-18 | Hiếu |  | Team agreed to increase team meeting time to help each other connect API and fix bugs | Having trouble connecting API between Front end and Back end causing slow project progress
3 | 2021-11-20 | Hoài | Speeding up the document progress to support Hieu in doing some Front end functions according to the progress of Sprint 3 | Complete some documents before the end of Sprint 3

## Sprint Task 4
Ahead Schedule
Sprint Task 4 | [10 empty] | End Task
[11 empty] | Late | [16 empty] | <- effort / day ->
Sprint Id | Backlog Id | Description | Owner | Start-Day | End-Day | Status | Story Points (Est.) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28
Sprint-4 |  |  | Team | 2021-11-22 | 2021-12-12 |  |  |  |  | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15 | 2021-12-16 | 2021-12-17 | 2021-12-18 | 2021-12-19
4 |  | Sprint 4 plan meeting | Team | 2021-11-22 | 2021-11-22 | Done | 7.5 | 7.5 | 0 | 2021-11-22: 0
4 |  | Sprint 4 backlog | Hieu | 2021-11-23 | 2021-11-23 | Done | 5 | 2.5 | 0 | 2021-11-22: 5; 2021-11-23: 0
4 |  | Design database sprint 4 | Phu | 2021-11-23 | 2021-11-24 | Done | 5 | 5 | 0 | 2021-11-22: 5; 2021-11-23: 2.5; 2021-11-24: 0
4 | PB08, PB09, PB21, PB40 | Design UI see report message, comment | Hoai | 2021-11-23 | 2021-11-27 | Done | 10 | 12.5 | 0 | 2021-11-22: 10; 2021-11-23: 10; 2021-11-24: 7.5; 2021-11-25: 5; 2021-11-26: 2.5; 2021-11-27: 0
4 |  | Design UI update personal | Hieu | 2021-11-24 | 2021-11-27 | Done | 10 | 10 | 0 | 2021-11-22: 10; 2021-11-23: 10; 2021-11-24: 7.5; 2021-11-25: 5; 2021-11-26: 2.5; 2021-11-27: 0
4 |  | Test case see report message and comment | Hieu | 2021-11-28 | 2021-12-01 | Done | 5 | 10 | 0 | 2021-11-22: 5; 2021-11-23: 5; 2021-11-24: 5; 2021-11-25: 5; 2021-11-26: 5; 2021-11-27: 5; 2021-11-28: 2.5; 2021-11-29: 2.5; 2021-11-30: 2.5; 2021-12-01: 0
4 |  | Test case update personal | Hoai | 2021-11-28 | 2021-11-29 | Done | 5 | 5 | 0 | 2021-11-22: 5; 2021-11-23: 5; 2021-11-24: 5; 2021-11-25: 5; 2021-11-26: 5; 2021-11-27: 5; 2021-11-28: 2.5; 2021-11-29: 0
4 |  | Code see report message and comment | Phu | 2021-11-25 | 2021-11-28 | Done | 7.5 | 10 | 0 | 2021-11-22: 7.5; 2021-11-23: 7.5; 2021-11-24: 7.5; 2021-11-25: 7.5; 2021-11-26: 5; 2021-11-27: 2.5; 2021-11-28: 0
4 |  | Code update personal | Phu | 2021-11-29 | 2021-12-02 | Done | 7.5 | 10 | 0 | 2021-11-22: 7.5; 2021-11-23: 7.5; 2021-11-24: 7.5; 2021-11-25: 7.5; 2021-11-26: 7.5; 2021-11-27: 7.5; 2021-11-28: 7.5; 2021-11-29: 7.5; 2021-11-30: 5; 2021-12-01: 2.5; 2021-12-02: 0
4 |  | Design UI see calendar | Hieu | 2021-12-02 | 2021-12-04 | Done | 10 | 7.5 | 0 | 2021-11-22: 10; 2021-11-23: 10; 2021-11-24: 10; 2021-11-25: 10; 2021-11-26: 10; 2021-11-27: 10; 2021-11-28: 10; 2021-11-29: 10; 2021-11-30: 10; 2021-12-01: 10; 2021-12-02: 7.5; 2021-12-03: 5; 2021-12-04: 0
4 |  | Design UI notify message and comment report by user | Hoai | 2021-11-30 | 2021-12-05 | Done | 12.5 | 15 | 0 | 2021-11-22: 12.5; 2021-11-23: 12.5; 2021-11-24: 12.5; 2021-11-25: 12.5; 2021-11-26: 12.5; 2021-11-27: 12.5; 2021-11-28: 12.5; 2021-11-29: 12.5; 2021-11-30: 10; 2021-12-01: 7.5; 2021-12-02: 5; 2021-12-03: 5; 2021-12-04: 2.5; 2021-12-05: 0
4 |  | Test case see calendar | Hoai | 2021-12-04 | 2021-12-06 | Done | 5 | 2.5 | 0 | 2021-11-22: 5; 2021-11-23: 5; 2021-11-24: 5; 2021-11-25: 5; 2021-11-26: 5; 2021-11-27: 5; 2021-11-28: 5; 2021-11-29: 5; 2021-11-30: 5; 2021-12-01: 5; 2021-12-02: 5; 2021-12-03: 5; 2021-12-04: 5; 2021-12-05: 5; 2021-12-06: 0
4 |  | Test case notify message and comment report by user | Hieu | 2021-12-05 | 2021-12-06 | Done | 5 | 5 | 0 | 2021-11-22: 5; 2021-11-23: 5; 2021-11-24: 5; 2021-11-25: 5; 2021-11-26: 5; 2021-11-27: 5; 2021-11-28: 5; 2021-11-29: 5; 2021-11-30: 5; 2021-12-01: 5; 2021-12-02: 5; 2021-12-03: 5; 2021-12-04: 5; 2021-12-05: 2.5; 2021-12-06: 0
4 |  | Code see calendar | Phu | 2021-12-03 | 2021-12-05 | Done | 7.5 | 7.5 | 0 | 2021-11-22: 7.5; 2021-11-23: 7.5; 2021-11-24: 7.5; 2021-11-25: 7.5; 2021-11-26: 7.5; 2021-11-27: 7.5; 2021-11-28: 7.5; 2021-11-29: 7.5; 2021-11-30: 7.5; 2021-12-01: 7.5; 2021-12-02: 7.5; 2021-12-03: 5; 2021-12-04: 2.5; 2021-12-05: 0
4 |  | Code notify message and comment report by user | Phu | 2021-12-06 | 2021-12-07 | Done | 5 | 5 | 0 | 2021-11-22: 5; 2021-11-23: 5; 2021-11-24: 5; 2021-11-25: 5; 2021-11-26: 5; 2021-11-27: 5; 2021-11-28: 5; 2021-11-29: 5; 2021-11-30: 5; 2021-12-01: 5; 2021-12-02: 5; 2021-12-03: 5; 2021-12-04: 5; 2021-12-05: 5; 2021-12-06: 2.5; 2021-12-07: 0
4 |  | Design UI search for user | Hieu | 2021-12-07 | 2021-12-10 | Done | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 7.5 | 5 | 2.5 | 0
4 |  | Code view information search for user | Phu | 2021-12-08 | 2021-12-09 | Done | 7.5 | 5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 5 | 0
4 |  | Code get report user or forum for admin | Phu | 2021-12-10 | 2021-12-10 | Done | 5 | 2.5 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
4 |  | Test report sprint 4 | Hoai | 2021-12-06 | 2021-12-10 | Done | 12.5 | 10 | 0 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 10 | 7.5 | 5 | 0
4 |  | Sprint 4 Review Meeting | Team | 2021-12-11 | 2021-12-11 | Done | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0
4 |  | Sprint 4 Retrospective Meeting | Team | 2021-12-12 | 2021-12-12 | Done | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0
[6 empty] | Total | 157.5 | 157.5 | 0 | 150 | 142.5 | 135 | 127.5 | 120 | 112.5 | 105 | 97.5 | 90 | 82.5 | 75 | 67.5 | 60 | 52.5 | 45 | 37.5 | 30 | 22.5 | 15 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Burn down | 157.5 | 160 | 0 | 150 | 142.5 | 135 | 130 | 122.5 | 115 | 107.5 | 105 | 100 | 92.5 | 85 | 80 | 70 | 62.5 | 52.5 | 45 | 37.5 | 27.5 | 15 | 7.5 | 0 | 0 | 0 |  |  |  |  | 0
[31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
Start-Day = XLOOKUP(0,[Day 1]:[Day 28],L8:AM8)
End-Day = XLOOKUP(0,[Day 1]:[Day 28],L8:AM8)

## Retrospective sprint 4
Retrospective Log Sprint 1
Sprint # | Date | Owner | Continue Doing | Start Doing | Stop Doing | Remarks
4 | 2021-11-24 | Team |  | The team increased the meeting with the team to speed up the progress before closing the Capstone project
4 | 2021-11-30 | Hoài |  | Hieu helped Hoai complete Vue's Chart function | Got an error when creating a Chart with Vue in the Admin section
4 | 2021-12-02 | Phú | Speed up the completion of documents and functions to meet the deadline for closing the project | Phu divides work specifically, clearly and motivates everyone to get the job done
4 | 2021-12-08 | Hiếu |  | The team assigns functions to help Hieu keep up with the schedule | Hieu still has many unfinished functions

## Sprint Report
Report Sprint 1
STT | Name member | Estimal | Actual
1 | Nguyen Thanh Phu | 70 | 67
2 | Dang Nguyen Bao Hoai | 70 | 72
3 | Nguyen Trung Hieu | 70 | 74
Tổng |  | 210 | 213
Report Sprint 2
STT | Name member | Estimal | Actual
1 | Nguyen Thanh Phu | 70 | 76
2 | Dang Nguyen Bao Hoai | 70 | 74
3 | Nguyen Trung Hieu | 70 | 73
Tổng |  | 210 | 223
Report Sprint 3
STT | Name member | Estimal | Actual
1 | Nguyen Thanh Phu | 52.5 | 55
2 | Dang Nguyen Bao Hoai | 52.5 | 51
3 | Nguyen Trung Hieu | 52.5 | 53
Tổng |  | 157.5 | 159
Report Sprint 4
STT | Name member | Estimal | Actual
1 | Nguyen Thanh Phu | 52.5 | 53
2 | Dang Nguyen Bao Hoai | 52.5 | 52
3 | Nguyen Trung Hieu | 52.5 | 55
Tổng |  | 157.5 | 160

## Impediment
Impediments |  | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On | Remarks
Id | Description
1 | Having no experience using Vue Js framework makes it a bit difficult to start Sprint 1 | Phú | 2021-09-10 | 1 |  | Hoài | Completed | Hieu instructs Hoai to use Vue js framework to start Sprint 1 | 2021-10-12
2 | No tools to support team work management, leading to unclear division of work | Phú | 2021-09-15 | 1 |  | Team | Completed | Unified use of Jira tool to manage the work of each team member | 2021-09-18
3 | The schedule of each member is not fixed, leading to not agreeing on the team meeting with the mentor | Hiếu | 2021-09-22 | 1 |  | Team | Completed | The whole team proposes to set aside a fixed time to meet with Mentor and create a meeting schedule with the team in advance | 2021-09-22
4 | Making User Story has not been completed, still has many problems | Phú | 2021-10-05 | 2 |  | Hiếu | Completed | Team together to complete User Story | 2021-10-08
5 | The group arranged to meet offline to work, but Hoai was at home isolated from covid-19 so he could not attend. | Hiếu | 2021-10-14 | 2 |  | Hoài | Completed | Hieu and Phu met offline to connect to the API for some functions, Hoai stayed at home to meet online to keep up with the team's progress | 2021-10-20
6 | Having trouble connecting API to Front end because of error | Hoài | 2021-10-22 | 2 |  | Phú | Completed | The team shared Phu's work to give Phu time to fix the error | 2021-10-28
7 | Too much study schedule, no time to get work done in Sprint 3 | Hoài | 2021-11-03 | 3 |  | Hiếu | Completed | Hoai does more of Hieu's work to reduce work and keep up with schedule. | 2021-11-05
8 | Unable to schedule a meeting with a mentor | Team | 2021-11-10 | 3 |  | Phú | Completed | The team agreed to increase the meeting time of the team to help each other complete the work | 2021-10-11
9 | Phu Having trouble installing Vue to test some functionality | Team | 2021-11-18 | 3 |  | Phú | Completed | The team guides Phu to install to complete the job | 2021-11-19
10 | Network problem, error connecting to API | Team | 2021-11-25 | 4 |  | Hiếu | Completed | Hold meetings to connect APIs and fix bugs together | 2021-11-30
11 | Difficulty using Vue Charts | Phú | 2021-12-02 | 4 |  | Hoài | Completed | Hieu helps Hoai complete the Chart function | 2021-12-04
12 | Work progress is being delayed compared to the project time | Phú | 2021-12-08 | 4 |  | Team | Completed | The team leader divides the work for each member and reminds everyone to hurry to complete their work | 2021-12-10