## Test report of Sprint 1
Project Name | School Connect Application
Creator | Nguyen Trung Hieu
Reviewer/ Approver | Dang Nguyen Bao Hoai
Date | September 30, 2021
|  | Round 1 |  | Round 2
No | Module Name | Pass | Fail | Pass | Fail | Not Run | N/A | Number of test cases
1 | Login Admin | 20 | 4 | 24 | 0 | 0 | 0 | 24
2 | Homepage Admin | 14 | 0 | 14 | 0 | 0 | 0 | 14
3 | Login User | 20 | 4 | 24 | 0 | 0 | 0 | 24
4 | Homepage User | 11 | 0 | 11 | 0 | 0 | 0 | 11
5 | Post | 4 | 1 | 5 | 0 | 0 | 0 | 5
6 | Post Event | 9 | 7 | 16 | 0 | 0 | 0 | 16
Total |  | 78 | 16 | 94 | 0 | 0 | 0 | 94
Test coverage |  | 100%
Test successful coverage Round 1 |  | 82.98%
Test successful coverage Round 2 |  | 100%

## Test report of Sprint 2
Project Name | School Connect Application
Creator | Nguyen Trung Hieu
Reviewer/ Approver | Dang Nguyen Bao Hoai
Date | October 28, 2021
|  | Round 1 |  | Round 2
No | Module Name | Pass | Fail | Pass | Fail | Not Run | N/A | Number of test cases
1 | View Account Managerment | 14 | 0 | 14 | 0 | 0 | 0 | 14
2 | Add Account | 46 | 3 | 49 | 0 | 0 | 0 | 49
3 | Update Account | 46 | 3 | 49 | 0 | 0 | 0 | 49
4 | View Forum Managerment | 14 | 0 | 14 | 0 | 0 | 0 | 14
5 | Add Forum | 13 | 1 | 14 | 0 | 0 | 0 | 14
6 | Update Forum | 18 | 1 | 19 | 0 | 0 | 0 | 19
7 | Comment | 4 | 0 | 4 | 0 | 0 | 0 | 4
8 | Censorship post and member | 6 | 0 | 6 | 0 | 0 | 0 | 6
9 | View Post | 2 | 0 | 2 | 0 | 0 | 0 | 2
10 | See report post and member | 4 | 0 | 4 | 0 | 0 | 0 | 4
Total |  | 167 | 8 | 175 | 0 | 0 | 0 | 175
Test coverage |  | 100%
Test successful coverage Round 1 |  | 95.43%
Test successful coverage Round 2 |  | 100%

## Test report of Sprint 3
Project Name | School Connect Application
Creator | Nguyen Trung Hieu
Reviewer/ Approver | Dang Nguyen Bao Hoai
Date | November 18, 2021
|  | Round 1 |  | Round 2
No | Module Name | Pass | Fail | Pass | Fail | Not Run | N/A | Number of test cases
1 | View Forum | 6 | 0 | 6 | 0 | 0 | 0 | 6
2 | View Forum Censor | 8 | 0 | 8 | 0 | 0 | 0 | 8
3 | Send message | 3 | 2 | 5 | 0 | 0 | 0 | 5
4 | Delete post, member, comment | 3 | 0 | 3 | 0 | 0 | 0 | 3
5 | Report message and comment | 2 | 0 | 2 | 0 | 0 | 0 | 2
6 | New post, message notification | 4 | 0 | 4 | 0 | 0 | 0 | 4
Total |  | 26 | 2 | 28 | 0 | 0 | 0 | 28
Test coverage |  | 100%
Test successful coverage Round 1 |  | 92.86%
Test successful coverage Round 2 |  | 100%

## Test report of Sprint 4
Project Name | School Connect Application
Creator | Nguyen Trung Hieu
Reviewer/ Approver | Dang Nguyen Bao Hoai
Date | December 8, 2021
|  | Round 1 |  | Round 2
No | Module Name | Pass | Fail | Pass | Fail | Not Run | N/A | Number of test cases
1 | Update profile | 20 | 4 | 24 | 0 | 0 | 0 | 24
2 | See calendar | 4 | 0 | 4 | 0 | 0 | 0 | 4
3 | View Forum See report message, comment | 2 | 0 | 2 | 0 | 0 | 0 | 2
4 | Block chat | 4 | 0 | 4 | 0 | 0 | 0 | 4
5 | Unblock chat | 3 | 0 | 3 | 0 |  |  | 3
6 | Change Password | 29 | 6 | 35 | 0 | 0 | 0 | 35
7 | Forgot Password | 20 | 2 | 22 | 0 | 0 | 0 | 22
Total |  | 82 | 12 | 94 | 0 | 0 | 0 | 94
Test coverage |  | 100%
Test successful coverage Round 1 |  | 87.23%
Test successful coverage Round 2 |  | 100%